## Phase 1
Day 1 | Day 2 | Day 3 | Day 4 | Day 5
Docker and Related Image – POC and Sandboxing | Continuation of understanding and learning of Kubernetes and Dockers.
Kubernetes, MiniCube/Kubectl(YAML File) – POC and Sandboxing | Installation of Docker and setup of other kubernetes services.
GITHUB creation – 3 Repositories(Learning – K3S, Architecting, Engineering K3S) --Aryaman | Making Docker file through alpine, using images and tags for building and running docker. - Siddharth
Aryaman will work with Both Sid and Chinmay to understand to Kubernetes and Docker in depth and help in POC and documenting. | Plan to eventually deploy host docker file in an Azure container. If not practical will utilise AWS instead.
Aryaman to get Line Manager Name(Budget holder name) and Billing Unit name, for installation of Docker and Kubernetes(KubeCTL/Minikube)
Sid – to research for the Kubernetes(KUBECTL and MINIkube) to identify the best resource for the project.
Harsh Sir has agreed to go ahead with above steps.
Harsh and Abhishek to discuss on setting up meeting with HPCC Guide for K3S and K3D
Harsh Sir has advised to create local KubeCTL/MINIKUBE code base file and only then plan for Virtual machines to run and test the python/ECL code.